## Tasks List
Sprint 1 | POSRA | [7 empty] | Rev 4 01/15/2014
|  |  | Team Member Name |  | Available Hours / Total Hours
Starts: 01/22/2014 |  |  | Nicholas |  | -6.5/30 | Igor | -3.5/30 | David | 3/30
Ends: 02/05/2014 |  |  | Konstantin |  | -3/30 | Nathan | -6.5/30 | Thomas | 0/30
|  |  | Weeks in Sprint: |  | 2
User Stories / Goals | Task | Assigned | Allocated Time |  | Meeting Days
|  |  |  | 2014-01-22 | 2014-01-24 | 2014-01-27 | 2014-01-29 | 2014-01-31 | 2014-02-03 | 2014-02-05
As a Developer, I need an architectural overview of OSRA’s processing, so I can understand the code base. | Generate/Compile Call Tree | Thomas | 1.5 |  | 0.5 | 0.5
| Generate/Compile Call Tree | Igor | 1.5 |  | 1
| Review call tree, and map to higher level processes | Konstantin | 4
| Review call tree, and map to higher level processes | Nathan | 4
| Diagram Processes of OSRA's processing of a Diagram | David | 3
| Identify locations for code insertion of other user stories in Process Diagram | Nicholas | 5 |  | 1 | 0.5
As a Developer, I need to review each aspect of OSRA’s architecture, so I can understand the code base. | Code review Higher level processes from Processing Diagram | Konstantin | 8
| Code review Higher level processes from Processing Diagram | Nicholas | 8
| Code review Higher level processes from Processing Diagram | Igor | 8 |  | 0.5 | 1
| Code review Higher level processes from Processing Diagram | Nathan | 8 |  | 1 | 1
| Code review Higher level processes from Processing Diagram | David | 8 |  | 2
| Code review Higher level processes from Processing Diagram | Thomas | 8 |  |  | 1
| Identify locations for code insertion of other user stories | Nicholas | 6.5
| Identify locations for code insertion of other user stories | Nathan | 6.5
| Identify external dependencies | Konstantin | 3
| Identify external dependencies | Nicholas | 3 |  |  | 0.5
| Identify external dependencies | Igor | 3
| Identify external dependencies | Nathan | 3
| Identify external dependencies | David | 3 |  |  | 2.5
| Identify external dependencies | Thomas | 3 |  |  | 0.5
As a Developer, I need to get a basic grasp of O-Chem, so I can better understand use cases. | Review O-Chem Chapter | Konstantin | 3
| Review O-Chem Chapter | Nicholas | 3
| Review O-Chem Chapter | Igor | 3 |  |  | 3
| Review O-Chem Chapter | Nathan | 3 |  |  | 1
| Review O-Chem Chapter | David | 3 |  |  | 1.5
| Review O-Chem Chapter | Thomas | 3
| Review Notes | Konstantin | 2
| Review Notes | Nicholas | 2
| Review Notes | Igor | 2
| Review Notes | Nathan | 2
| Review Notes | David | 2
| Review Notes | Thomas | 2
| Generate Cheat/Reference sheet for diagrams | Mathew | 2.5
| O-Chem - to - SMILES | Konstantin | 0.5
| O-Chem - to - SMILES | Nicholas | 0.5
| O-Chem - to - SMILES | Igor | 0.5
| O-Chem - to - SMILES | Nathan | 0.5
| O-Chem - to - SMILES | David | 0.5
| O-Chem - to - SMILES | Thomas | 0.5
As a Developer, I need workflow and processes for the github repo, so I can collaborate on c | Organize structure of repo | Nicholas | 0.5
| Designate naming convention for branchs and code submition | Nicholas | 0.5
| Create and enforce workflow for pulls/pushes/merges | Nicholas | 0.5
As a Developer, I need a testing enviroment and test documentation, so I can better contribu | Create template for bug submissions | Konstantin | 0.5
| Create build/test server in windows | Igor | 5
| Create initial test cases | Igor | 0.5
| Create Development Workflow | Nathan | 1
| Create Development Workflow | Nicholas | 1
| Create Development Workflow | Igor | 1
As a Developer, I need to have consolidated documentation from other developers, so I can be | Create location for consolidated documentation | Nathan | 0.5
| Create template for indevidual's documentation | Nathan | 0.5
As a Developer, I need to understand SMILES notation and .SD file structure, so I can desing | Review .SD File contents | Konstantin | 0.5
| Review .SD File contents | Thomas | 0.5
| Review SMILES notation documentations | Konstantin | 0.5
| Review SMILES notation documentations | Nicholas | 0.5
| Review SMILES notation documentations | Igor | 0.5
| Review SMILES notation documentations | Nathan | 0.5
| Review SMILES notation documentations | David | 0.5
| Review SMILES notation documentations | Thomas | 0.5
As a User, I want to have a data structure for encoding polymers in “Smile Notation”, so I c | Create DB Schema | Thomas | 2
| Create DB Schema | Konstantin | 2
| Create DB Schema | Igor | 1
| Design DB Access Layer | Thomas | 1
| Design DB Access Layer | Konstantin | 1
| Design DB Access Layer | Igor | 1
| Design Object Model | Thomas | 1
| Design Object Model | Igor | 1
| Design Object Model | Konstantin | 1
|  |  | 160 | 0/160 | 6/160 | 19/160 | 19/160 | 19/160 | 19/160 | 19/160
|  |  | 160 | 0 | 6 | 19 | 19 | 19 | 19 | 19
|  |  |  | 160 | 160 | 160 | 160 | 160 | 160 | 160
|  |  |  | 0 | [5 empty] | 160
|  |  |  | Burn Up | Expected | Ideal
Started Bookkeeping folder and files

## Backlog
Backlog | POSRA
User Stories | MoSCoW | User Stories | Assigned Sprint
As a Developer, I need an architectural overview of OSRA’s processing, so I can understand the code base. | M | 13 | 1
As a Developer, I need to review each aspect of OSRA’s architecture, so I can understand the code base. | M | 20 | 1
As a Developer, I need to get a basic grasp of O-Chem, so I can better understand use cases. | M | 5 | 1
As a Developer, I need workflow and processes for the github repo, so I can collaborate on code | M | 5 | 1
As a Developer, I need a testing enviroment and test documentation, so I can better contribute to the codebase | M | 20 | 1
As a Developer, I need to have consolidated documentation from other developers, so I can better contribute to the codebase | M | 13 | 1
As a Developer, I need to understand SMILES notation and .SD file structure, so I can desing the smile data structure. | M | 5 | 1
As a User, I want to be able to detect Par. in Chemical Diagram, so I can work with polymers | M | 20 | 2
As a User, I want to be able to detect Brackets in Chemical Diagrams, so I can work with polymers | S | 20 | 3
As a User, I want to be able to detect subscripts for polymer diagrams, so I can work with polymers | M | 13 | 4
As a User, I want to be able to detect “R-Notation”, so I can work with polymers | W | INF | -
As a User, I want to have a data structure for encoding polymers in “Smile Notation”, so I can work with polymers | M | 13 | 1
As a User, I need an .SD files from the diagram for each sub molecule in the diagram, so I can work with polymers | S | 5 | 2

## Scrum Board
Backlog |  | Sprint 1
|  | Not Started |  | In Progrers |  | Finished
As a User, I want to be able to detect Par. in Chemical Diagram, so I can work with polymers | 20 |  |  | As a Developer, I need an architectural overview of OSRA’s processing, so I can understand the code base. | 13
| M |  |  |  | M
As a User, I want to be able to detect Brackets in Chemical Diagrams, so I can work with polymers | 20 |  |  | As a Developer, I need to review each aspect of OSRA’s architecture, so I can understand the code base. | 20
| S |  |  |  | M
As a User, I want to be able to detect subscripts for polymer diagrams, so I can work with polymers | 13 |  |  | As a Developer, I need to get a basic grasp of O-Chem, so I can better understand use cases. | 5
| M |  |  |  | M
As a User, I want to be able to detect “R-Notation”, so I can work with polymers | INF | As a Developer, I need workflow and processes for the github repo, so I can collaborate on code | 5
| W |  | M
|  | As a Developer, I need a testing enviroment and test documentation, so I can better contribute to the codebase | 20
M
|  | As a Developer, I need to have consolidated documentation from other developers, so I can better contribute to the codebase | 13
M
|  | As a Developer, I need to understand SMILES notation and .SD file structure, so I can desing the smile data structure. | 5
M
|  | As a User, I want to have a data structure for encoding polymers in “Smile Notation”, so I can work with polymers | 13
M

## Names-Hours
| Hours/Week | Total for Sprint | Planning + Meetings/Week | Role Responsabilities | Other Non-Sprint Hours | Total Not Dev Hours Implemented
Nicholas | 15 | 30 | 4 | 1.5 | 0 | 24.5
Konstantin | 15 | 30 | 4 | 3 | 0 | 23
Igor | 15 | 30 | 4 | 3 | 0 | 23
Nathan | 15 | 30 | 4 | 1.5 | 0 | 24.5
David | 15 | 30 | 4 | 3 | 0 | 23
Thomas | 15 | 30 | 4 | 1 | 0 | 25
Mathew | 8 | 16 | 3 | 0 | 0 | 13

## ToDo
TO DO:
2013-10-10 | Make Uer Story for "Other"
New User Story for BackEnd.