## Tasks List
Sprint 4 | POSRA | [7 empty] | Rev 4 04/08/2014
|  |  | Team Member Name |  | Available Hours / Total Hours
Starts: 04/09/2014 |  |  | Nicholas |  | 14.5/30 | Igor | 7/30 | David | 13/30
Ends: 04/23/2014 |  |  | Konstantin |  | 15/30 | Nathan | 6.5/30 | Thomas | 22/30
|  |  | Matthew |  | 10/16 |  | Weeks in Sprint: |  | 2
User Stories / Goals | Task | Assigned | Allocated Time |  | Meeting Days
|  |  |  | 2014-04-09 | 2014-04-11 | 2014-04-14 | 2014-04-16 | 2014-04-18 | 2014-04-21 | 2014-04-23
As a User, I want to be able to detect brackets in Chemical Diagram, so I can work with polymers | Detect Bracket Direction | David | 4 | 4
| Detect Bracket Direction | Nicholas | 4
| Detect Left and Right Bracket Pairs | David | 4 | 4
| Detect Left and Right Bracket Pairs | Nicholas | 4
| Detect Horizontal Brackets | David | 2 | 2
| Detect Horizontal Brackets | Nicholas | 2 | 2
As a User, I need SMILES Strings for output, so I can store polymers as a string | Write Finalized Document outlining the final SMILES Format for Polymers | nathan | 2 | 2
As a Developer, I need documentation of my code, so that I, or someone else, can reference my code later | Design documentation template | Igor | 6
| Design documentation template | nathan | 6
| Determine portions of code to document | Igor | 2
| Determine portions of code to document | Nathan | 2
| Document code as needed | Igor | 8
| Document code as needed | Nathan | 8
As a Developer, I need a Data Model to store polymerms, so that I can create a website to interact with the database | Finalize list of what data needs to be stored | Matthew |  | 0
| Finalize list of what data needs to be stored | Thomas |  | 0
| Update Data Model | Matthew | 3 | 3
| Update Data Model | Konstantin | 3 | 3
| Implement Basic/Initial version of Data Model | Thomas | 3 | 3
| Implement Basic/Initial version of Data Model | Konstantin | 3
As a User, I need a website to be able to access the database of polymers, so I can search(-) and import (+) polymers | Compile list of technologies from IBM | Konstantin | 1 | 1
| Create basic API framework | Konstantin |  | 0
| Create basic API framework | Igor |  | 0
| Create basic API framework | nathan |  | 0
| Create basic API framework | nicholas
| Create basic API framework | David
| Create basic API framework | Thomas
| Implement basic insert/search API's | Konstantin
| Implement basic insert/search API's | Igor
| Implement basic insert/search API's | Nathan
| Implement basic insert/search API's | nicholas |  | 0
| Implement basic insert/search API's | David
| Implement basic insert/search API's | Thomas |  | 0
| Setup Server enviroment | Konstantin |  | 0
| Setup Server enviroment |  |  | 0
|  |  | 67 | 24 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 67 | 24 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 67 | [5 empty] | 0
|  |  |  | Burn Down |  | Ideal
Started Bookkeeping folder and files

## Backlog
Backlog | POSRA
User Stories | MoSCoW | User Stories | Assigned Sprint
As a User, I want to be able to detect brackets in Chemical Diagram, so I can work with polymers | M |  | 4 - 5
As a User, I want to be able to detect subscripts for polymer diagrams, so I can work with polymers | M |  | 5
As a Developer, I need to understand the OpenBable library, so I can understand how to leverage it and work around it | M |  | 5 - 6
As a User, I need an .SD files from the diagram for each sub molecule in the diagram, so I can work with polymers | W |  | 6
As a User, I need SMILES Strings for output, so I can store polymers as a string | M |  | 4
As a User, I want to be able to detect “R-Notation”, so I can work with polymers | S |  | 6
As a User, I need a website to be able to access the database of polymers, so I can search(-) and import (+) polymers | M |  | 4 - 6
As a Developer, I need a Data Model to store polymerms, so that I can create a website to interact with the database | M |  | 4 - 7
As a Developer, I need documentation of my code, so that I, or someone else, can reference my code later | M |  | 4
Finished | POSRA
User Stories | MoSCoW | User Stories | Assigned Sprint

## Scrum Board
Backlog |  | Sprint 4
|  | Not Started |  | In Progrers | Finished
As a User, I need an .SD files from the diagram for each sub molecule in the diagram, so I can work with polymers | W | As a User, I want to be able to detect brackets in Chemical Diagram, so I can work with polymers | M
| 0 |  | 0
As a User, I need SMILES Strings for output, so I can store polymers as a string | M | As a User, I need SMILES Strings for output, so I can store polymers as a string | M
| 0 |  | 0
As a User, I want to be able to detect “R-Notation”, so I can work with polymers | S | As a Developer, I need a Data Model to store polymerms, so that I can create a website to interact with the database | M
| 0 |  | 0
As a User, I want to be able to detect subscripts for polymer diagrams, so I can work with polymers | M | As a User, I need a website to be able to access the database of polymers, so I can search(-) and import (+) polymers | M
| 0 |  | 0
|  | As a Developer, I need documentation of my code, so that I, or someone else, can reference my code later | M
0

## Names-Hours
| Hours/Week | Total for Sprint | Planning + Meetings/Week | Role Responsabilities | Other Non-Sprint Hours | Total Not Dev Hours Implemented
Nicholas | 15 | 30 | 4 | 1.5 | 0 | 24.5
Konstantin | 15 | 30 | 4 | 4 | 0 | 22
Igor | 15 | 30 | 4 | 3 | 0 | 23
Nathan | 15 | 30 | 4 | 1.5 | 0 | 24.5
David | 15 | 30 | 4 | 3 | 0 | 23
Thomas | 15 | 30 | 4 | 1 | 0 | 25
Matthew | 8 | 16 | 3 | 0 | 0 | 13

## ToDo
TO DO:
2013-10-10 | Make Uer Story for "Other"
New User Story for BackEnd.