## Tasks List
Sprint 2 | POSRA | [7 empty] | Rev 4 01/15/2014
|  |  | Team Member Name |  | Available Hours / Total Hours
Starts: 02/05/2014 |  |  | Nicholas |  | 24.5/30 | Igor | 23/30 | David | 23/30
Ends: 02/19/2014 |  |  | Konstantin |  | 22/30 | Nathan | 24.5/30 | Thomas | 25/30
|  |  | Mathew |  | 13/16 |  | Weeks in Sprint: |  | 2
User Stories / Goals | Task | Assigned | Allocated Time |  | Meeting Days
|  |  |  | 2014-02-05 | 2014-02-07 | 2014-02-10 | 2014-02-12 | 2014-02-14 | 2014-02-17 | 2014-02-19
| Create build/test server in windows | Thomas
| Create build/test server in windows | Igor
| Create initial test cases | Igor
| Create Development Workflow | Thomas
| Create Development Workflow | Konstantin
As a Developer, I need to understand SMILES notation and .SD file structure, so I can desing the smile data structure.
As a User, I want to have a data structure for encoding polymers in “Smile Notation”, so I can work with polymers
As a Developer, I need to research possible methods for detecting parenthesis, so I can find the best way to implement parenthesis | Review implementation of POTRACE in OSRA | Nicholas
| Review implementation of POTRACE in OSRA | Nathan
| Brain Storm methods ( Point Dencity, Detect as character) | Konstantin
| Brain Storm methods ( Point Dencity, Detect as character) | Nicholas
| Brain Storm methods ( Point Dencity, Detect as character) | Igor
| Brain Storm methods ( Point Dencity, Detect as character) | Nathan
| Brain Storm methods ( Point Dencity, Detect as character) | David
| Brain Storm methods ( Point Dencity, Detect as character) | Thomas
| Brain Storm methods ( Point Dencity, Detect as character) | Mathew
| Try Various brainstormed methods for detecting parenthesis | Nicholas
| Try Various brainstormed methods for detecting parenthesis | Nathan
| Try Various brainstormed methods for detecting parenthesis | Igor
As a Developer, I need to research methods for submiting end and repeating groups for smile conversion, so I can know how to generate SMILES for different segments | Review implementation of OpenBabel in OSRA | Konstantin
| Review implementation of OpenBabel in OSRA | Nicholas
| Brain Storm methods for submiting segments | Konstantin
| Brain Storm methods for submiting segments | Nicholas
| Brain Storm methods for submiting segments | Igor
| Brain Storm methods for submiting segments | Nathan
| Brain Storm methods for submiting segments | David
| Brain Storm methods for submiting segments | Thomas
| Brain Storm methods for submiting segments | Mathew
| Try Various brainstormed methods for submiting segments | Konstantin
| Try Various brainstormed methods for submiting segments | Nicholas
| Try Various brainstormed methods for submiting segments | David
As a Developer, I need to have a x32 based development enviroment, so I can modify, compile, and test the application | Install Cygwin, and all need libraries | Thomas
| Install Cygwin, and all need libraries | Igor
| Find and download all external libraries | Thomas
| Find and download all external libraries | Igor
| Configure and compile | Thomas
| Configure and compile | Igor
| Install and Configure Eclipse | Thomas
| Install and Configure Eclipse | Igor
| Install and Configure Eclipse | Konstantin
|  |  | 0 | 0/0 | 0/0 | 0/0 | 0/0 | 0/0 | 0/0 | 0/0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | [5 empty] | 0
|  |  |  | Burn Up | Expected | Ideal
Started Bookkeeping folder and files

## Backlog
Backlog | POSRA
User Stories | MoSCoW | User Stories | Assigned Sprint
As a Developer, I need a testing enviroment and test documentation, so I can better contribute to the codebase | M | 20 | 1-2
As a Developer, I need to understand SMILES notation and .SD file structure, so I can desing the smile data structure. | M | 5 | 2
As a User, I want to be able to detect Par. in Chemical Diagram, so I can work with polymers | M | 20 | 2
As a User, I want to be able to detect Brackets in Chemical Diagrams, so I can work with polymers | S | 20 | 3
As a User, I want to be able to detect subscripts for polymer diagrams, so I can work with polymers | M | 13 | 4
As a User, I want to be able to detect “R-Notation”, so I can work with polymers | W | INF | -
As a User, I want to have a data structure for encoding polymers in “Smile Notation”, so I can work with polymers | M | 13 | 2
As a User, I need an .SD files from the diagram for each sub molecule in the diagram, so I can work with polymers | S | 5 | 3
As a Developer, I need to understand the POTRACE library, so I can understand how to leverage it and work around it | M |  | 2
As a Developer, I need to understand the OpenBable library, so I can understand how to leverage it and work around it | M |  | 2
As a Developer, I need to have a x64 based development enviroment, so I can modify, compile, and test the application | M |  | 2
Finished | POSRA
User Stories | MoSCoW | User Stories | Assigned Sprint
As a Developer, I need an architectural overview of OSRA’s processing, so I can understand the code base. | M | 13 | 1
As a Developer, I need to review each aspect of OSRA’s architecture, so I can understand the code base. | M | 20 | 1
As a Developer, I need to get a basic grasp of O-Chem, so I can better understand use cases. | M | 5 | 1
As a Developer, I need workflow and processes for the github repo, so I can collaborate on code | M | 5 | 1
As a Developer, I need to have consolidated documentation from other developers, so I can better contribute to the codebase | M | 13 | 1

## Scrum Board
Backlog |  | Sprint 2
|  | Not Started |  | In Progrers |  | Finished
As a User, I want to be able to detect Par. in Chemical Diagram, so I can work with polymers | 20 |  |  | As a Developer, I need a testing enviroment and test documentation, so I can better contribute to the codebase | 20
| M |  |  |  | M
As a User, I want to be able to detect Brackets in Chemical Diagrams, so I can work with polymers | 20 | As a Developer, I need to understand SMILES notation and .SD file structure, so I can desing the smile data structure. | 5
| S |  | M
As a User, I want to be able to detect subscripts for polymer diagrams, so I can work with polymers | 13 | As a User, I want to have a data structure for encoding polymers in “Smile Notation”, so I can work with polymers | 13
| M |  | M
As a User, I want to be able to detect “R-Notation”, so I can work with polymers | INF | As a Developer, I need to understand the POTRACE library, so I can understand how to leverage it and work around it | 0
| W |  | M
As a User, I need an .SD files from the diagram for each sub molecule in the diagram, so I can work with polymers | 5 | As a Developer, I need to understand the OpenBable library, so I can understand how to leverage it and work around it | 0
| S |  | M

## Names-Hours
| Hours/Week | Total for Sprint | Planning + Meetings/Week | Role Responsabilities | Other Non-Sprint Hours | Total Not Dev Hours Implemented
Nicholas | 15 | 30 | 4 | 1.5 | 0 | 24.5
Konstantin | 15 | 30 | 4 | 4 | 0 | 22
Igor | 15 | 30 | 4 | 3 | 0 | 23
Nathan | 15 | 30 | 4 | 1.5 | 0 | 24.5
David | 15 | 30 | 4 | 3 | 0 | 23
Thomas | 15 | 30 | 4 | 1 | 0 | 25
Mathew | 8 | 16 | 3 | 0 | 0 | 13

## ToDo
TO DO:
2013-10-10 | Make Uer Story for "Other"
New User Story for BackEnd.